WEEKLY STATUS REPORT

|  |  |  |  |
| --- | --- | --- | --- |
| **Reporting period:** | **17/11/2022 to 23/11/2022** | **Project title:** | **Faster & Smarter Disease Prediction** |
| **Date of report:** | **25/11/2022** | **Report author:** | **Amit Sharma** |

STATUS SUMMARY

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Narrative Summary of** **Status** | **Schedule:** | **Amber** | **Overall:** | **GREEN** |

PROJECT MILESTONE STATUS REVIEW

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Project Milestones** | **Status** | **Baseline Completion Date** | **Expected Completion Date** | **Issues Exist (Yes/No)** |
| *Planning Phase* | **Finished** | 12/10/2022 | 12/10/2022 | No |
| *Development and Execution* | **In Progress** | 19/11/2022 | 2/12/2022 | Yes |
| *Presentation and closing* | Not Started |  |  |  |

PLANNED ACTIVITIES AND ACCOMPLISHMENTS

|  |
| --- |
| ***Accomplishments this Week:*** |
| * *Including Deep learning and other algorithms -* ***Completed*** * *Disease categorization/Regrouping changes -* ***Completed*** * *Finalize the Template for the algorithm and set the measuring parameters for quality-* ***Completed*** * *Start with Tableau graphs and One page of Dashboard –* ***In Progress*** |

|  |
| --- |
| ***Planned Actions for Next Week:*** |
| * *Started working on initial Data grouping in Tableau* * *Start working on the Documentation and Presentation* |

|  |  |  |  |
| --- | --- | --- | --- |
| Darshan Patel | Rajan Atulkumar Patel | Urali Virajsinh Rana | Amit Sharma |
| (0789282) | (0789953) | (0789945) | (0794488) |

1. | P a g e

PROJECT ISSUES SUMMARY

|  |  |  |  |
| --- | --- | --- | --- |
| ***Priority*** | ***Issue Description*** | ***Impact Summary (Milestone, Schedule Scope, Resources, Space…)*** | ***Action Steps/Resolutions*** |
| Medium | **Date Field/Seasons - Data Engineering** | Better grouping of data and bigger buckets for classification | Season dates of 2022 is used to categorize the data |
| Medium | **Algorithms showing lower Accuracy rates** | 2 algorithms (logistic and SVC) both showing very low accuracy, this leading to addition of XG Boost into the list | Adding XG Boost as a new algorithm and exploring Deep learning |
| Medium | **Too many Categories to Predict** | Accuracy is getting impacted on algorithms | Regrouping of the categories into broader groups |
| Low | **Too many projects and Exams are impacting the schedule of the project** | Too many projects – in Ethics, Project management and Marketing going parallel | Team need to work more in parallel to finish the work on time |

Team Contributions

|  |  |  |
| --- | --- | --- |
| ***Team members*** | ***Responsibility and work*** | ***Next steps*** |
| **Urali Rana and Amit Sharma** | Start working on the presentation and finalize the outcome prediction | Finalize the Algorithm and See what features are important |
| **Darshan Patel and Rajan Patel** | Tableau work and initial graphs and Project Report | Start working on the Report |

1. | P a g e

|  |  |  |  |
| --- | --- | --- | --- |
| Darshan Patel | Rajan Atulkumar Patel | Urali Virajsinh Rana | Amit Sharma |
| (0789282) | (0789953) | (0789945) | (0794488) |